## ProcessFlow
Lithography
LPCVD
Etching / Cleaning
Diffusion / Anneal
Implant
Metal Deposition
IMP | Backside and Frontside Implant dummy wafer
ET1 | Etch rate wafer for frontside contact oxide etch
ET2 | Etch rate wafer for TEOS passivation layer etch
Step # | Description with Tool Needs | Estimated Time (hours) | Cost per hour ($) | Estimated Cost ($)
1 | RCA Clean, RCA Wetbench | 1 | 60 | 60
2 | Protective Oxide Growth, Bruce Furnace Tube #1 (approx. 1000A) | 3 | 45 | 135
3 | Coat Frontside with Photoresist, CEE Handspinner | 0.25 | 45 | 11.25
4 | Etch Oxide (Backside), HF Wetbench, 10:1HF | 0.25 | 0 | 0
5 | Remove Photoresist, PRS2000 Wetbench | 1 | 60 | 60
6 | Photo 1 - Backside Alignment marks, Karl Suss MA56 | 1 | 60 | 60
| CEE Hand Coater and Developer | 0.5 | 45 | 22.5
7 | Etch Silicon alignment marks, DryTech Quad | 1 | 85 | 85
8 | Strip Photoresist, PRS 2000 | 0.75 | 60 | 45
9 | Etch Remaining Oxide | 0.5 | 0 | 0
10 | RCA Clean, RCA Wetbench | 1 | 60 | 60
11 | Backside Screening Oxide Growth, Bruce Furnace Tube #4 (approx. 500A) | 3 | 45 | 135
| include IMP: measure oxide thickness |  |  | 0
12 | Backside Phosphorus Implant, Varian 350D Implanter (E=33keV, Dose = 5e14) | 4 | 150 | 600
| include IMP |  |  | 0
13 | Strip Oxide, BOE Chemical Bench | 0.5 | 0 | 0
| include IMP (use for etch rate wafer): measure junction depth |  |  | 0
14 | RCA Clean, RCA Wetbench | 1 | 60 | 60
15 | Backside Oxide Growth, Bruce Furnace Tube #4 (approx. 100A) | 3 | 45 | 135
| include ET1: measure oxide thickness |  |  | 0
| include IMP |  |  | 0
16 | Backside LTO Deposition, LPCVD (approx. 4900A) | 3.5 | 100 | 350
| include ET1: measure total oxide thickness |  |  | 0
| include IMP |  |  | 0
17 | Backside Protection Silicon Nitride Growth, LPCVD Furnace (approx. 1500A) | 3.5 | 100 | 350
include IMP: measure nitride thickness
| include ET1 |  |  | 0
18 | Coat Backside Film Stack with Photoresist (CEE Hand Coater) | 0.25 | 45 | 11.25
include ET1
19 | Dry Etch of Nitride on the frontside of the wafer, DryTech Quad | 0.5 | 60 | 30
include IMP
| include ET1 |  |  | 0
20 | Strip Photoresist, Branson Asher | 0.75 | 60 | 45
include ET1
21 | Wet Etch for grown and deposited oxide on the frontside, BOE Chemical Bench | 0.5 | 60 | 30
| include IMP |  |  | 0
22 | Photo 2 - Frontside Alignment marks, Karl Suss MA56 | 3 | 60 | 180
| CEE Hand Coater and Developer | 0.75 | 45 | 33.75
23 | Etch Silicon alignment marks, DryTech Quad | 0.75 | 85 | 63.75
24 | Strip Photoresist, PRS 2000 | 0.75 | 50 | 37.5
25 | RCA Clean, RCA Wetbench | 1 | 60 | 60
26 | Frontside Screening Oxide Growth, Bruce Furnace Tube #4 (approx. 300A) | 3 | 45 | 135
26 | include IMP: measure oxide thickness |  |  | 0
27 | Photo 3 - Frontside Well Definition, Karl Suss MA56 | 2 | 60 | 120
27 | CEE Hand Coater and Developer | 0.5 | 45 | 22.5
DO NOT include IMP, better measurements can be taken with a blanket implant
28 | Frontside Boron Well Implant, Varian 350D Implanter (E=~33keV, Dose=1e15) | 3 | 150 | 450
| include IMP |  |  | 0
29 | Strip Photoresist, PRS 2000 | 0.75 | 50 | 37.5
30 | Etch Oxide (damaged from implant) Frontside, BOE chemical bath | 0.5 | 0 | 0
30 | use IMP for etch rate wafer, measure junction depth from frontside implant |  |  | 0
31 | RCA Clean, RCA Wetbench | 1 | 60 | 60
32 | Frontside Oxide Growth, Bruce Furnace Tube #4 (approx. 100A) | 3 | 45 | 135
| include ET1: measure oxide thickness |  |  | 0
33 | Frontside LTO Deposition, LPCVD (approx. 5000A) | 3.5 | 100 | 350
| include ET1: measure total oxide thickness |  |  | 0
34 | Anneal, AG610A/B RTA (1100C for 3min) | 0.75 | 130 | 97.5
35 | Backside Oxide Etch to remove oxide deposited on the nitride, BOE Cup Etch) | 0.75 | 0 | 0
36 | Strip Backside Silicon Nitride, Hot Phosphorus Bench | 1.5 | 60 | 90
| include IMP |  |  | 0
37 | Photo 4 - Backside Contact Etch, Karl Suss MA56 | 1 | 60 | 60
| CEE Hand Coater and Developer | 0.5 | 45 | 22.5
38 | Etch Oxide (backside contacts), BOE Chemical Bench Cup Etch | 0.75 | 0 | 0
| use IMP for etch rate wafer, then include and measure junction depth from step 16 |  |  | 0
39 | Strip Photoresist, PRS 2000 | 0.75 | 50 | 37.5
40 | Backside Aluminum Deposit, CVC601 (approx. 5000A) | 12 | 45 | 540
41 | Photo 5 - Backside Aluminum Etch, Karl Suss MA56 | 1 | 60 | 60
| CEE Hand Coater and Developer | 0.5 | 45 | 22.5
42 | Wet Etch Backside Aluminum, Aluminum Etch Bench | 0.5 | 60 | 30
43 | Strip Photoresist, PRS 2000 | 0.75 | 50 | 37.5
44 | Coat Backside with Photoresist, CEE Hand Coater | 0.5 | 45 | 22.5
45 | Photo 6 - Frontside Well Contact, Karl Suss MA56 | 0.5 | 60 | 30
| CEE Hand Coater and Developer | 0.5 | 80 | 40
46 | Etch Oxide - frontside contacts, BOE Chemical Bench | 0.5 | 0 | 0
use ET1 for etch rate wafer
47 | Strip Photoresist, PRS 2000 | 0.75 | 50 | 37.5
48 | Frontside Aluminum Deposition, CVC601 (approx. 5000A) | 12 | 45 | 540
49 | Photo 7 - Frontside Contact Etch, Karl Suss MA56 | 0.5 | 60 | 30
47 | CEE Hand Coater and Developer | 0.5 | 80
50 | Wet Etch of Frontside Aluminum, Aluminum Etch Bench | 0.5 | 60 | 30
51 | Strip Photoresist, PRS 2000 | 0.75 | 60 | 45
52 | Frontside Passivation Layer Deposition of LTO, LPCVD (approx. 500A) | 3.5 | 145 | 507.5
52 | include ET2: measure for oxide thickness |  |  | 0
53 | Photo 8 - Passivation Layer Trim, Karl Suss MA56 | 0.5 | 60 | 30
53 | CEE Hand Coater and Developer, | 1 | 80 | 80
54 | Etch Passivation Layer, BOE Chemical Bench Cup Etch | 0.5 | 0 | 0
54 | use ET2 for etch rate wafer |  |  | 0
55 | Strip Photoresist, PRS 2000 | 0.75 | 50 | 37.5
| Total Time and Cost for Device Fabrication: | 98.25 |  | 6397.5
| Total Time and Cost for Experimental Wafer Processing: | 38 |  | 2430
| Total Time and Cost for One Run: | 136.25 |  | 8827.5
| Total Time and Cost for Two Runs: | 234.5 |  | 15225

## ProcessFlowDetails
Step | Process | Details | Include | Record | Target
1 | RCA Clean | RCA Wetbench | Device Wafers | - | -
2 | Protective Oxide Growth | Bruce Furnace, Tube 1, Recipe #311 | Device Wafers | Oxide Thickness | 1000A
3 | Coat Frontside with Photoresist | CEE Handspinner | Device Wafers | - | -
4 | Etch Backside Oxide | 10:1 BOE, 2 minutes (586 A/min) | Device Wafers | - | -
5 | Remove Photoresist | PRS-2000 Bench | Device Wafers | - | -
6 | Photo 1 - Backside Alignment marks | Coat HMDS on CEE Hand Coater | Device Wafers | - | -
7 |  | Coat Resist on CEE Hand Coater
8 |  | Bake at 90C for 60s
9 |  | Expose on KarlSuss MA56
10 |  | Bake at 120C for 60s
11 |  | Develop on CEE Hand Developer
7 | Etch Silicon Alignment Marks | DryTech Quad, use carrier wafers, recipe "polysilicon" - 1 minute | Device Wafers | - | -
8 | Strip Photoresist | PRS-2000 Bench | Device Wafers | - | -
9 | Etch Remaining Oxide | HF Wetbench, 10:1 BOE, 2 minutes (586 A/min) | Device Wafers | - | -
10 | RCA Clean, RCA Wetbench | RCA Wetbench | Device Wafers | - | -
11 | Backside Screening Oxide Growth | Bruce Furnace, Tube 4, Recipe #458 | Device Wafers + IMP | Oxide Thickness | 500A
12 | Backside Phosphorus Implant | Varian 350D Implanter, Dose = 5e14, Energy = 33keV, P31 | Device Wafers + IMP | - | -
13 | Strip Oxide, BOE Chemical Bench | HF Wetbench, 10:1 BOE, 1 minute (586 A/min) | Device Wafers + IMP | Junction Depth | < 0.75um
14 | RCA Clean | RCA Wetbench | Device Wafers + IMP | - | -
15 | Backside Oxide Growth | Bruce Furnace, Tube 4, Recipe #450 | Device Wafers + IMP + ET1 | Oxide Thickness | 100A
16 | Backside LTO Deposition | LPCVD Tube #1, Factory LTO Recipe, 53 minutes | Device Wafers + IMP + ET1 | Oxide Thickness | 5000A
17 | Backside Protection Silicon Nitride Growth | LPCVD Tube #2, Factory Nitride Recipe, 23 minutes | Device Wafers + IMP + ET1 | Nitride Thickness | 1500A
18 | Backside Photoresist Protective Coating | Coat Resist on CEE Hand Coater | Device Wafers + IMP + ET1 | - | -
19 |  | Bake at 90C for 120s
19 | Dry Etch of Nitride on the frontside of the wafer | DryTech Quad, Nitride Recipe, 2min (stop on LTO) | Device Wafers + IMP + ET1 | - | -
20 | Oxide Etch frontside oxide | HF Wetbench, 10:1 BOE, 4 minutes (1600 A/min, 586 A/min - T) | Device Wafers + IMP + ET1 | - | -
21 | Strip Photoresist | PRS-2000 Bench | Device Wafers + IMP + ET1 | - | -
22 | Photo 2 - Frontside Alignment marks | Coat HMDS on CEE Hand Coater | Device Wafers | - | -
23 |  | Coat Resist on CEE Hand Coater
24 |  | Bake at 90C for 60s
25 |  | Expose on KarlSuss MA56
26 |  | Bake at 120C for 60s
27 |  | Develop on CEE Hand Developer
23 | Etch Silicon alignment marks | DryTech Quad, use carrier wafer, recipe "polysilicon" - 1 minute | Device Wafers | - | -
24 | Strip Photoresist | PRS-2000 Bench | Device Wafers | - | -
25 | RCA Clean | RCA Wetbench | Device Wafers + IMP | - | -
26 | Frontside Screening Oxide Growth | Bruce Furnace, Tube 4, Recipe #456 | Device Wafers + IMP | Oxide Thickness | 300A
27 | Photo 3 - Frontside Well Definition | Coat HMDS on CEE Hand Coater | Device Wafers | - | -
28 |  | Coat Resist on CEE Hand Coater
29 |  | Bake at 90C for 60s
30 |  | Expose on KarlSuss MA56
31 |  | Bake at 120C for 60s
32 |  | Develop on CEE Hand Developer
28 | Frontside Boron Well Implant | Varian 350D Implanter, Dose = 1e15, Energy = 33keV, BF2 | Device Wafers + IMP
29 | Strip Photoresist | PRS-2000 Bench | Device Wafers | - | -
30 | Etch Oxide (damaged from implant) Frontside | HF Wetbench, 10:1 BOE, 2 minutes (586 A/min) | Device Wafers + IMP | Junction Depth, rs | < 0.6um
31 | RCA Clean, RCA Wetbench | RCA Wetbench | Device Wafers + IMP + ET1 | - | -
32 | Frontside Oxide Growth | Bruce Furnace, Tube 4, Recipe #450 | Device Wafers + IMP + ET1 | Oxide Thickness | 100A
33 | Frontside LTO Deposition | LPCVD Tube #1, Factory LTO Recipe, 38 minutes | Device Wafers + IMP + ET1 | Oxide Thickness | 5000A
34 | Anneal | AG610A/B RTA, 1100C, 3 minutes | Device Wafers | - | -
35 | Backside Oxide Etch (remove any oxide on the nitride) | 10:1 BOE Cup Etch, 1 minute (586 A/min) | Device Wafers + IMP + ET1 | - | -
36 | Strip Backside Silicon Nitride | Hot Phosphorus Bench, 45 min | Device Wafers + IMP + ET1 | - | -
37 | Photo 4 - Backside Contact Etch | Coat HMDS on CEE Hand Coater | Device Wafers | - | -
38 |  | Coat Resist on CEE Hand Coater
39 |  | Bake at 90C for 60s
40 |  | Expose on KarlSuss MA56
41 |  | Bake at 120C for 60s
42 |  | Develop on CEE Hand Developer
38 | Etch Oxide (backside contacts) | 10:1 BOE Cup Etch, 3.5 minutes (1600 A/min, 586 A/min), strip IMP | Device Wafers + IMP + ET1 | Junction Depths, rs | < 1.0um, < 0.75um
39 | Strip Photoresist | PRS-2000 Bench | Device Wafers | - | -
40 | Backside Aluminum Deposit | CVC601 Sputter, 15sccm Argon, Power = 1500W, 18 minutes | Device Wafers + ET1 (taped) | Al Thickness | 5000A
41 | Photo 5 - Backside Aluminum Etch | Coat HMDS on CEE Hand Coater | Device Wafers | - | -
42 |  | Coat Resist on CEE Hand Coater
43 |  | Bake at 90C for 60s
44 |  | Expose on KarlSuss MA56
45 |  | Bake at 120C for 60s
46 |  | Develop on CEE Hand Developer
42 | Wet Etch of Backside Aluminum | Aluminum Etch Bench, 1 minute 20 seconds | Device Wafers + ET1 | - | -
43 | Strip Photoresist | PRS-2000 Bench | Device Wafers | - | -
44 | Backside Photoresist Protective Coating | CEE Hand Coater | Device Wafers | - | -
45 | Photo 6 - Frontside Well Contact | Coat HMDS on CEE Hand Coater | Device Wafers | - | -
46 |  | Coat Resist on CEE Hand Coater
47 |  | Bake at 90C for 60s
48 |  | Expose on KarlSuss MA56
49 |  | Bake at 120C for 60s
50 |  | Develop on CEE Hand Developer
46 | Etch Oxide - Frontside Contacts | 10:1 BOE, 3.5 minutes (1600 A/min, 586 A/min), use ET1 | Device Wafers + ET1 | - | -
47 | Strip Photoresist | PRS-2000 Bench | Device Wafers | - | -
48 | Frontside Aluminum Deposition | CVC601 Sputter, 15sccm Argon, Power = 1500W, 18 minutes | Device Wafers + ET2 (taped) | Al Thickness | 5000A
49 | Photo 7 - Frontside Contact Etch | Coat HMDS on CEE Hand Coater | Device Wafers | - | -
50 |  | Coat Resist on CEE Hand Coater
51 |  | Bake at 90C for 60s
52 |  | Expose on KarlSuss MA56
53 |  | Bake at 120C for 60s
54 |  | Develop on CEE Hand Developer
50 | Wet Etch of Frontside Aluminum | Aluminum Etch Bench, 1 minute 20 seconds
51 | Strip Photoresist, PRS 2000 | PRS-2000 Bench | Device Wafers | - | -
52 | Frontside Passivation Layer Deposition of LTO | LPCVD Tube #1, Factory LTO Recipe, 4 minutes | Device Wafers + ET2 | Oxide Thickness | 500A
53 | Photo 8 - Passivation Layer Trim | Coat HMDS on CEE Hand Coater | Device Wafers | - | -
54 |  | Coat Resist on CEE Hand Coater
55 |  | Bake at 90C for 60s
56 |  | Expose on KarlSuss MA56
57 |  | Bake at 120C for 60s
58 |  | Develop on CEE Hand Developer
54 | Etch Passivation Layer, BOE Chemical Bench | "Pad Etch" Cup Etch, 15 minutes (38 A/min), use ET2 | Device Wafers + ET2 | - | -
55 | Strip Photoresist, PRS 2000 | PRS-2000 Bench | Device Wafers | - | -
End

## JunctionDepthScreening
Truncated Steps for Implant Profile Test Wafer | Notes | Estimated Time | Hourly Rate | Total Cost
1 - RCA Clean | RCA Wetbench | 0.75 | 60 | 45
11 - Backside Screening Oxide Growth (500A) | Bruce Furnace, Tube 4, Recipe #458 | 3 | 45 | 135
12 - Backside Phosphorus Implant | Varian 350D Implanter, Dose = 1e14, Energy = 33keV, P31 | 0.75 | 150 | 112.5
13 - Strip Oxide (500A, 2min) | HF Wetbench, 10:1 BOE, 1 minute (586 A/min) | 0.25 | 60 | 15
14 - RCA Clean | RCA Wetbench | 0.75 | 60 | 45
15 - Backside Interface Oxide Growth (100A) | Bruce Furnace, Tube 4, Recipe #450 | 3 | 45 | 135
16 - Backside LTO Deposition (4900A) | LPCVD Tube #1, Factory LTO Recipe, 53 minutes | 3 | 100 | 300
17 - Silicon Nitride Growth (1500A) | LPCVD Tube #2, Factory Nitride Recipe, 23 minutes | 3 | 100 | 300
18 - Coat Backside with Photoresist | Coat Resist on CEE Hand Coater Bakce at 90C for 120s | 0.5 | 60 | 30
19 - Dry Etch of Nitride on the Frontside (1500A) | Lam490, Factory Nitride Etch recipe (stop on LTO) | 0.75 | 80 | 60
20 - Remove Photoresist | Branson Asher
21 - Pad Etch for Frontside Oxide (~5000A, 20min) | HF Wetbench, 10:1 BOE, 3.5 minutes (1600 A/min, 586 A/min - T) | 0.5 | 60 | 30
25 - RCA Clean | RCA Wetbench | 0.75 | 60 | 45
26 - Frontside Screening Oxide Growth (300A) | Bruce Furnace, Tube 4, Recipe #456 | 3 | 45 | 135
28 - Frontside Boron Implant | Varian 350D Implanter, Dose = 1e15, Energy = 33keV, BF2 | 0.75 | 150 | 112.5
30 - Etch Oxide (1000A, 3.5min) | HF Wetbench, 10:1 BOE, 2 minutes (586 A/min) | 0.25 | 60 | 15
31 - RCA Clean | RCA Wetbench | 0.75 | 60 | 45
32 - Frontside Interface Oxide Growth (100A) | Bruce Furnace, Tube 4, Recipe #450 | 3 | 45 | 135
35 - Backside Oxide Etch | 10:1 BOE, 1 minute (586 A/min) | 0.5 | 60 | 30
36 - Strip Backside Nitride | Hot Phos bath, 45 min (87 A/min) | 2 | 60 | 120
Etch all Oxide | 10:1 BOE bath, 5 minutes (586 A/min) | 0.75 | 60 | 45
Total Steps = 18 | Total Time = | 28 | Total Cost = | 1890
No anneal is necessary, all the thermal steps were necessary to obtain the correct surface concentration and / or junction depth. |  | (~1.5 weeks of work)
From here, sheet resistance will be measured on a 4pt. Probe station, then junction depth will be measured by groove and stain. | Measuring steps are not billed tool time.

## DoubleAlignmentPractice
To create and test the alignment procedure (front to back), the Karl Suss MA150 will be used.
It should require 6 hours of tool time (to be generous and practice on more than one wafer). The cost for that would be $360.
The testing would also require photoresist coating and development to make sure the alignment worked.
It should require about 2 hours of spin-coating time and 2 hours of developing (to be generous). The cost for that would be $180.
The total cost for the alignment test wafers' processing should be $540.